PROJECT MANAGEMENT COMPREHENSIVE REPORT

Project Title: Development and Implementation of an Enterprise AI Knowledge Assistant using MCP Architecture for Project Intelligence and Operational Support

Prepared By: MBA Candidate / Project Manager

Date: June 26, 2026

Course: Advanced Project Management

2. Executive Summary

This report outlines the project management framework for developing an Enterprise AI Knowledge Assistant leveraging Model Context Protocol (MCP) architecture. Designed to dismantle information silos across Azure DevOps (ADO), Microsoft Teams, and Outlook, this AI solution serves as a unified intelligence layer for global delivery teams. The project operates on a ₹50,000,000 budget with an 8-month timeline. By applying advanced digital strategy and data analytics principles, the project transitions manual Quarterly Business Review (QBR) and Weekly Business Review (WBR) reporting into automated, AI-driven workflows.

3. Introduction to Enterprise AI Knowledge Management

Modern enterprise resource planning and delivery require instant access to contextual data. Currently, critical project intelligence is fragmented. The proposed AI Knowledge Assistant utilizes MCP to establish a standardized, secure communication protocol between the central LLM and disparate data sources (ADO, Teams, Outlook, enterprise knowledge bases).

4. Business Problem Statement

Global delivery teams and POD leaders spend approximately 25-30% of their weekly bandwidth manually aggregating project statuses, tracking sprint velocities, and searching for historical documentation across disconnected systems, leading to delayed decision-making and operational inefficiencies.

5. Current Challenges in Project Information Access

- Data Silos: ADO tracks tasks, Teams hosts communications, and Outlook manages schedules; there is no cross-platform querying.

- Manual Reporting: Synthesizing WBR, MBR, and QBR documents requires exhaustive manual data extraction.

- Knowledge Attrition: Historical project insights and POD structures are lost in unstructured repositories.

6. Project Objectives

- Improve project visibility across all PODs and Sub-PODs by 40%.

- Reduce information retrieval time from an average of 20 minutes to under 30 seconds.

- Fully automate the generation of foundational WBR, MBR, and QBR drafts.

- Deploy a scalable MCP architecture integrating ADO, Teams, and Outlook within 8 months.

7. Project Scope

In Scope:

- Development of the AI Chatbot interface.

- MCP server deployment for secure data brokering.

- API integrations: Azure DevOps, MS Teams, Outlook.

- Automated parsing of internal documentation and project repositories.

- Implementation of SpecKit Driven Development via Harness Engineering Platform.

Out of Scope:

- Migration of legacy data into ADO.

- Integration with third-party HR or payroll systems.

- Hardware procurement (cloud-hosted on existing infrastructure).

8. Project Assumptions

- Existing enterprise APIs (Graph API, ADO REST API) will remain stable during development.

- Workfast and GitHub Copilot will increase developer productivity by 20%.

- End-users have standard M365 and ADO access credentials.

9. Project Constraints

- Security: Must adhere to strict enterprise data privacy protocols; zero training of public LLMs on internal proprietary data.

- Budget: Capped at ₹50,000,000.

- Time: Must be deployed before the Q1 FY27 enterprise planning cycle.

10. Success Criteria and KPIs

- Adoption Rate: 80% of Delivery Leads and TPMs utilizing the bot daily within Month 1 of launch.

- Accuracy: AI responses achieve a $\ge 95\%$ accuracy rating in UAT.

- Latency: Query response time $\le 3$ seconds.

11. Project Charter

Project Sponsor: Chief Information Officer (CIO)

Total Budget: ₹50,000,000

Timeline: July 1, 2026 – February 28, 2027

Key Deliverables: MCP Infrastructure, Integrations (ADO/Teams/Outlook), NLP Chatbot Interface, UAT Sign-off.

Milestones:

- M1: Architecture Approved (Month 1)

- M2: Core Integrations Complete (Month 4)

- M3: Beta Release to POD Leaders (Month 6)

- M4: Enterprise Launch (Month 8)

12. Stakeholder Identification & 13. Power-Interest Matrix

Table 1: Stakeholder Power-Interest Matrix

| Stakeholder Group | Power | Interest | Strategy |
| --- | --- | --- | --- |
| CIO / Senior Mgmt | High | High | Manage Closely |
| Delivery Leads / TPMs | High | High | Manage Closely |
| POD / Sub-POD Leaders | Medium | High | Keep Informed |
| Developers / QA | Low | High | Keep Informed |
| Enterprise IT Security | High | Low | Keep Satisfied |
| Microsoft Teams Users | Low | Low | Monitor |

14. Communication Management Plan

Table 2: Communication Matrix

| Artifact | Audience | Frequency | Channel | Owner |
| --- | --- | --- | --- | --- |
| Executive Dashboard | Senior Mgmt | Monthly | Outlook / PowerBI | Project Manager |
| Sprint Demo | Delivery Leads | Bi-Weekly | MS Teams | Scrum Master |
| Tech Sync | Dev & IT Sec | Weekly | Harness / Teams | AI Architect |
| Go-Live Announcement | All Users | Once | Email Blast | Change Mgmt |

15. Work Breakdown Structure (WBS) & 16. WBS Dictionary

Table 3: Work Breakdown Structure

| WBS Code | Phase / Task | Description |
| --- | --- | --- |
| 1.0 | Requirements & Design | Scope definition and architecture blueprinting |
| 1.1 | MCP Architecture Design | Mapping LLM to data sources securely |
| 2.0 | Development Integrations | Building API pipelines |
| 2.1 | ADO Integration | Fetching sprints, stories, velocity |
| 2.2 | Teams & Outlook API | Syncing communications and calendars |
| 3.0 | AI Core Development | LLM tuning and conversational logic |
| 3.1 | QBR/WBR Automation Logic | Prompt engineering for reporting templates |
| 4.0 | Testing & Deployment | Validation and enterprise rollout |
| 4.1 | UAT & Security Audit | Red-teaming the AI and verifying permissions |

17. Activity List with Dependencies & 18. Gantt Chart

Table 4: Gantt Chart and Dependencies

| Activity | Description | Duration | Dependencies |
| --- | --- | --- | --- |
| A | Requirement Gathering | 3 Wks | - |
| B | MCP Architecture Design | 4 Wks | A |
| C | ADO Integration | 6 Wks | B |
| D | Teams & Outlook Integration | 5 Wks | B |
| E | Knowledge Repo Processing | 4 Wks | B |
| F | AI Chatbot Core Logic | 7 Wks | C, D, E |
| G | Security Audit & QA | 3 Wks | F |
| H | UAT | 2 Wks | G |
| I | Training & Go-Live | 2 Wks | H |

19. PERT Analysis

Table 5: PERT Estimation (Duration in Weeks)

| Activity | Optimistic (O) | Most Likely (M) | Pessimistic (P) | Expected Time (Te​) |
| --- | --- | --- | --- | --- |
| B (Architecture) | 3 | 4 | 6 | 4.17 |
| C (ADO) | 4 | 6 | 9 | 6.17 |
| F (AI Logic) | 5 | 7 | 11 | 7.33 |
| G (Security) | 2 | 3 | 5 | 3.17 |

Calculation utilized:

$$T_e = \frac{O + 4M + P}{6}$$

20. CPM Analysis & 21. Critical Path Identification

Network Paths:

- Path 1: A $\rightarrow$ B $\rightarrow$ C $\rightarrow$ F $\rightarrow$ G $\rightarrow$ H $\rightarrow$ I (Duration: 3+4+6+7+3+2+2 = 27 Weeks)

- Path 2: A $\rightarrow$ B $\rightarrow$ D $\rightarrow$ F $\rightarrow$ G $\rightarrow$ H $\rightarrow$ I (Duration: 3+4+5+7+3+2+2 = 26 Weeks)

Critical Path: Path 1.

Managerial Insight: ADO Integration (C) represents the most complex data transformation task and dictates the project timeline.

22. Project Crashing Analysis

Table 6: Crashing Matrix

| Activity | Normal Dur. | Crash Dur. | Normal Cost (₹) | Crash Cost (₹) | Cost / Wk (₹) |
| --- | --- | --- | --- | --- | --- |
| C (ADO) | 6 Wks | 4 Wks | 4,000,000 | 5,500,000 | 750,000 |
| F (AI Core) | 7 Wks | 5 Wks | 8,000,000 | 9,800,000 | 900,000 |

Recommendation: If the project falls behind, Activity C should be crashed first due to its lower marginal crash cost.

23. Resource Planning & 24. Resource Leveling

Key Resources: Project Manager, Scrum Master, 3 AI Engineers, 2 Backend Devs, ADO Specialist, QA Team.

Resource Leveling Issue: AI Engineers are over-allocated during Week 15 (simultaneously finalizing integrations and beginning Chatbot Core).

Resolution: Stagger the commencement of Activity F by leveraging 1 week of float on Activity D, ensuring AI Engineers can focus exclusively on ADO data mapping before moving to NLP prompt engineering.

25. Risk Management Plan & 26. Risk Register

Table 7: Risk Register

| Risk ID | Description | Prob | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| R01 | Hallucinations in QBR data | High | High | Strict RAG implementation; mandate human-in-the-loop validation for financial metrics. |
| R02 | MCP Server Downtime | Low | High | Deploy redundant server clusters across distinct Azure availability zones. |
| R03 | API Rate Limiting (Teams) | Med | Med | Implement intelligent caching and exponential backoff algorithms. |
| R04 | User Adoption Resistance | Med | High | Gamify adoption; demonstrate immediate time-savings to TPMs. |

27. Waterfall Project Approach vs 28. Agile Project Management Approach

Waterfall Viability: A predictive approach is useful for the initial MCP architecture setup and hardware provisioning, where requirements are rigid and security compliance is non-negotiable.

Agile Application (Selected):

- Scrum Roles: AI Architect (Product Owner), Scrum Master, Dev Team.

- Sprint Planning: 2-week iterations utilizing SpecKit Driven Development.

- Backlog Examples: "As a TPM, I want to query the current sprint velocity so I can update the WBR."

29. Waterfall vs Agile Comparison

For enterprise AI, strict Waterfall fails because prompt engineering and NLP behavior cannot be perfectly defined upfront. Agile allows the team to ingest user feedback during Beta testing and refine the LLM's contextual understanding of enterprise-specific terminology (e.g., internal POD acronyms).

30. Earned Value Analysis (EVA)

Snapshot at Week 14 (Planned budget spent to date: ₹25,000,000).

- Planned Value (PV): ₹25,000,000

- Earned Value (EV): ₹22,000,000

- Actual Cost (AC): ₹24,000,000

Calculations:

- $$SV = EV - PV = -3,000,000$$

(Behind Schedule)

- $$CV = EV - AC = -2,000,000$$

(Over Budget)

- $$SPI = EV / PV = 0.88$$

- $$CPI = EV / AC = 0.91$$

Interpretation: The project is currently operating at 88% of planned speed and yielding ₹0.91 of value per rupee spent. The integration complexities of legacy internal documentation repositories caused minor delays. Corrective action involves utilizing GitHub Copilot more aggressively for boilerplate API connection code.

31. Project Monitoring and Control Mechanisms

- Harness Engineering Platform: Automated CI/CD pipeline metrics to monitor deployment frequencies and bug rates.

- Sprint Retrospectives: Bi-weekly alignment to address bottlenecks in data querying logic.

32. Project Closure Plan

- Operational Transition: Handover of MCP infrastructure maintenance to internal IT Operations.

- Administrative Closure: Finalize vendor billing for external LLM API usage.

- Knowledge Transfer: Document the SpecKit architecture for future AI expansions.

33. Lessons Learned

- Data Quality: Internal documentation was highly unstructured, requiring more pre-processing than anticipated. Future AI projects must enforce stricter data governance prior to kickoff.

- Tooling: GitHub Copilot significantly accelerated routine backend development, offsetting some architectural delays.

34. Managerial Recommendations

Leveraging enterprise data analytics backgrounds is crucial when designing this architecture. Do not treat the AI as a standalone tool; integrate it into the existing digital strategy ecosystem. To ensure the automated WBR/QBR drafts are trusted by senior management, the AI must explicitly cite its internal data sources (e.g., linking directly to the ADO ticket or Outlook thread) within its output.

35. Conclusion

The implementation of the Enterprise AI Knowledge Assistant via MCP architecture represents a paradigm shift in how project intelligence is consumed. Despite inherent risks in API integrations and data hallucinations, rigorous Agile methodologies and strict RAG protocols ensure a secure, highly efficient operational support tool that will drastically reduce administrative overhead for global delivery teams.