- PROJECT MANAGEMENT – Project Submission

Project Title: Go-To-Market (GTM) Strategy for Samsung Ballie in India

Prepared By: MBA Candidate / Project Manager

Date: June 26, 2026

Course: Advanced Project Management & Strategy

2. Executive Summary

This report outlines the comprehensive project management plan for the Go-To-Market (GTM) strategy of Samsung Ballie, an AI-powered smart home robotic companion, in the Indian market. The project is budgeted at ₹40,000,000 over a 6-month timeline, targeting a Diwali festival launch. The strategy utilizes a hybrid project management approach, blending Waterfall methodologies for fixed-timeline distribution logistics and Agile frameworks for dynamic digital marketing and software localization. The report details the critical path, risk mitigation strategies, and earned value analytics required to execute a high-stakes consumer technology launch successfully.

3. Introduction to the Project

The Indian smart home market is experiencing a compound annual growth rate (CAGR) of 18%, presenting a lucrative opportunity for premium AI robotics. Samsung Ballie represents a shift from passive smart speakers to proactive home companions. This project encompasses market research, pricing strategy, distribution network setup, digital marketing, and software localization to ensure Ballie resonates with the Indian premium consumer segment.

4. Business Problem Statement

Despite high smartphone penetration, Indian consumers exhibit hesitation toward premium smart home robotics due to perceived lack of utility, privacy concerns, and lack of localized voice support (e.g., Hindi/Hinglish NLP). The business problem is to design a GTM strategy that overcomes these adoption barriers, establishes a robust Omni-channel distribution network, and achieves a targeted market penetration of 10,000 units within the first year of launch.

5. Project Objectives

- Strategic: Position Samsung Ballie as the market leader in the Indian premium smart home segment.

- Financial: Achieve ₹400,000,000 in gross revenue (10,000 units at ₹40,000 average selling price) in Year 1.

- Operational: Establish distribution partnerships with Croma, Reliance Digital, and Amazon India within 4 months.

- Technical: Complete Hindi/Hinglish software localization integration prior to launch.

6. Project Scope

In Scope:

- Consumer sentiment and pricing elasticity research.

- Software localization coordination (voice UI/UX).

- Marketing campaign development (digital, print, experiential).

- Retail channel partner onboarding and inventory logistics planning.

- Launch event execution.

Out of Scope:

- Hardware design, engineering, and manufacturing.

- Post-launch customer service operations (handled by existing Samsung care network).

- Global market launches outside of India.

7. Project Assumptions and Constraints

Assumptions:

- Target demographic (upper-middle-class urban consumers) has stable disposable income.

- Regulatory approvals from the Bureau of Indian Standards (BIS) will be obtained without delays.

- Global supply chain can fulfill the initial 15,000 unit inventory requirement.

Constraints:

- Time: Must launch by Week 24 to capitalize on Diwali retail traffic.

- Cost: Strictly capped at ₹40,000,000.

- Quality: AI voice recognition must hit a 95% accuracy rate for regional accents.

8. Project Success Criteria

- Schedule Adherence: Launch executed by the target date (SPI $\ge$ 1.0 at project close).

- Budget Adherence: Total project cost remains under ₹40,000,000 (CPI $\ge$ 1.0).

- Quality Metrics: Beta testing shows $>85\%$ positive sentiment regarding localized features.

- Stakeholder Satisfaction: Sign-off from Samsung India executive board without major revisions.

9. Project Charter

Project Name: Samsung Ballie India GTM

Project Sponsor: VP of Consumer Electronics, Samsung India

Project Manager: [Name]

Total Budget: ₹40,000,000

Start Date: July 1, 2026

End Date: December 15, 2026

Key Deliverables:

- Market Strategy Document

- Localized Software Beta

- Signed Retailer Agreements

- Marketing Campaign Assets

- Official Launch Event

Milestones:

- M1: Strategy Approval (Week 4)

- M2: Retailer Contracts Signed (Week 12)

- M3: Marketing Assets Finalized (Week 16)

- M4: Product Launch (Week 24)

10. Stakeholder Identification

Effective stakeholder management is critical for a matrix organization.

- Internal: Project Sponsor, Marketing Team, Software Dev Team, Supply Chain Division.

- External: Retail Partners (Croma, Amazon), PR Agencies, Regulatory Bodies (BIS), Target Consumers.

11. Stakeholder Power-Interest Matrix

Table 1: Stakeholder Matrix

| Stakeholder | Power | Interest | Strategy (PMP Framework) |
| --- | --- | --- | --- |
| Project Sponsor | High | High | Manage Closely: Regular 1-on-1 briefings, steering committees. |
| Retail Partners | High | High | Manage Closely: Collaborative planning, margin negotiations. |
| Software Dev Team | High | Medium | Keep Satisfied: Clear requirements, milestone tracking. |
| PR Agency | Medium | High | Keep Informed: Weekly status reports, asset sharing. |
| BIS (Regulators) | High | Low | Keep Satisfied: Ensure strict compliance, submit docs early. |
| Target Consumers | Low | High | Keep Informed: Focus groups, teaser marketing campaigns. |

Managerial Insight: Retail partners possess high power due to shelf-space control. They must be treated as project partners rather than mere vendors.

12. Communication Plan

Table 2: Communication Matrix

| Information/Report | Target Audience | Frequency | Format/Channel | Owner |
| --- | --- | --- | --- | --- |
| Executive Status Report | Project Sponsor | Bi-Weekly | Dashboard / PDF | Project Manager |
| Sprint Review | Marketing / Dev | Weekly | Zoom Meeting | Scrum Master |
| Vendor Coordination | PR / Retailers | Weekly | Email / Phone | Channel Manager |
| Risk Register Update | Steering Committee | Monthly | Presentation | Project Manager |

13. Work Breakdown Structure (WBS)

The WBS decomposes the GTM strategy into manageable work packages, enabling accurate cost and schedule estimation.

14. Detailed WBS Dictionary

Table 3: Complete WBS Table

| WBS Code | Task Name | Description | Deliverable |
| --- | --- | --- | --- |
| 1.0 | Initiation & Strategy | Project kickoff and planning |  |
| 1.1 | Market Research | Competitor analysis & pricing elasticity | Research Report |
| 1.2 | GTM Strategy | Finalizing target segments & positioning | Strategy Document |
| 2.0 | Localization (Agile) | Software adaptation for India |  |
| 2.1 | Voice AI Training | Hinglish NLP dataset integration | Trained Model |
| 2.2 | Beta Testing | User acceptance testing in target market | UAT Report |
| 3.0 | Distribution & Logistics | Channel setup |  |
| 3.1 | Partner Negotiations | Contract structuring with retailers | Signed Contracts |
| 3.2 | Inventory Staging | Moving stock to regional warehouses | Stock Delivery |
| 4.0 | Marketing & PR | Demand generation |  |
| 4.1 | Asset Creation | TVCs, digital ads, print media | Media Assets |
| 4.2 | Media Buying | Purchasing ad slots across platforms | Media Plan |
| 5.0 | Launch Operations | Execution of the launch event |  |
| 5.1 | Event Setup | Venue booking, stage design | Event Readiness |
| 5.2 | Go-Live | Official product announcement | Press Release |

15. Project Activity List

Predecessor dependencies established for network diagramming.

- A: Market Research (Start)

- B: GTM Strategy (Depends on A)

- C: Voice AI Training (Depends on B)

- D: Partner Negotiations (Depends on B)

- E: Beta Testing (Depends on C)

- F: Inventory Staging (Depends on D)

- G: Asset Creation (Depends on B)

- H: Media Buying (Depends on G)

- I: Launch Operations (Depends on E, F, H)

16. Gantt Chart

Table 4: Complete Gantt Chart Table

| Activity | Start Week | End Week | Duration | Dependencies | Resource |
| --- | --- | --- | --- | --- | --- |
| A. Market Research | W1 | W3 | 3 Wks | None | Marketing Analyst |
| B. GTM Strategy | W4 | W5 | 2 Wks | A | Project Manager |
| C. Voice AI Training | W6 | W13 | 8 Wks | B | Dev Team |
| D. Partner Negotiation | W6 | W11 | 6 Wks | B | Sales Lead |
| E. Beta Testing | W14 | W17 | 4 Wks | C | QA Team |
| F. Inventory Staging | W12 | W17 | 6 Wks | D | Supply Chain |
| G. Asset Creation | W6 | W12 | 7 Wks | B | Creative Agency |
| H. Media Buying | W13 | W16 | 4 Wks | G | PR Agency |
| I. Launch Operations | W18 | W21 | 4 Wks | E, F, H | Event Team |

Managerial Insight: The Gantt chart visualizes parallel execution. While development (C, E) occurs, sales (D, F) and marketing (G, H) must execute concurrently to meet the Diwali deadline.

17. PERT Network Diagram

To account for uncertainty in software and marketing tasks, a Program Evaluation and Review Technique (PERT) analysis is utilized.

Table 5: PERT Table (Duration in Weeks)

| Activity | Optimistic (O) | Most Likely (M) | Pessimistic (P) | Expected Time (Te​) |
| --- | --- | --- | --- | --- |
| A | 2 | 3 | 4 | 3.00 |
| B | 1.5 | 2 | 2.5 | 2.00 |
| C | 6 | 8 | 12 | 8.33 |
| D | 4 | 6 | 8 | 6.00 |
| E | 3 | 4 | 6 | 4.17 |
| F | 5 | 6 | 7 | 6.00 |
| G | 5 | 7 | 10 | 7.17 |
| H | 3 | 4 | 5 | 4.00 |
| I | 3 | 4 | 5 | 4.00 |

Formula used: $T_e = \frac{O + 4M + P}{6}$

18. CPM Analysis & 19. Critical Path Identification

Table 6: CPM Network Analysis (Using $T_e$ rounded to nearest week for simplicity)

| Path | Activities | Total Duration (Weeks) |
| --- | --- | --- |
| Path 1 | A $\rightarrow$ B $\rightarrow$ C $\rightarrow$ E $\rightarrow$ I | 3 + 2 + 8 + 4 + 4 = 21 Weeks |
| Path 2 | A $\rightarrow$ B $\rightarrow$ D $\rightarrow$ F $\rightarrow$ I | 3 + 2 + 6 + 6 + 4 = 21 Weeks |
| Path 3 | A $\rightarrow$ B $\rightarrow$ G $\rightarrow$ H $\rightarrow$ I | 3 + 2 + 7 + 4 + 4 = 20 Weeks |

Critical Path Identification:

Paths 1 and 2 are currently parallel critical paths at 21 weeks. This indicates high project risk; any delay in either Software Localization (C, E) or Distribution Logistics (D, F) will delay the final launch.

20. Project Duration Analysis

The total expected duration is 21 weeks. Given our hard deadline of 24 weeks (Diwali), we have 3 weeks of project float. However, because we have dual critical paths, project management must apply strict variance monitoring to both development and supply chain tracks.

21. Project Crashing Analysis

If early delays consume the 3-week float, schedule compression will be required. We analyze crashing costs to determine the most cost-effective way to reduce the project timeline.

Table 7: Project Crashing Table

| Activity | Normal Time | Crashed Time | Normal Cost (₹) | Crashed Cost (₹) | Crash Cost / Week (₹) |
| --- | --- | --- | --- | --- | --- |
| C. Voice AI | 8 Wks | 6 Wks | 5,000,000 | 6,500,000 | 750,000 |
| E. Beta Test | 4 Wks | 3 Wks | 1,000,000 | 1,400,000 | 400,000 |
| F. Logistics | 6 Wks | 5 Wks | 3,000,000 | 4,000,000 | 1,000,000 |

Managerial Insight: If schedule compression is required, Activity E (Beta Testing) should be crashed first as it provides the lowest crash cost per week (₹400,000) on a critical path.

22. Resource Allocation

Resources must be assigned effectively to prevent bottlenecks. The marketing agency is heavily utilized in Weeks 6-12. The Dev team is strictly allocated to Activity C and E.

23. Resource Leveling Plan

During Week 10, the PR and Marketing lead was scheduled to oversee both Asset Creation (G) and preliminary Launch Operations planning (I), resulting in a 150% allocation overload.

Table 8: Resource Leveling Table

| Resource | Original Allocation | Over-allocation Issue | Resolution Strategy (Leveling) | Adjusted Allocation |
| --- | --- | --- | --- | --- |
| Dev Team | 100% (Weeks 6-13) | None | N/A | 100% |
| Mktg Lead | 150% (Week 10-12) | Managing G and early I | Delay early launch planning (I) utilizing float on Path 3. | 100% |
| QA Team | 120% (Week 14) | Beta Test volume | Hire contract QA testers for Week 14-15 | 100% core + Temps |

24. Risk Identification

Risk management involves identifying technical, commercial, and operational threats. Risks were identified using Delphi technique and historical data from previous Samsung India launches.

25. Risk Register

Table 9: Risk Register

| Risk ID | Risk Description | Probability | Impact | Score (PxI) | Mitigation Strategy | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R01 | NLP fails to recognize regional dialects | High (4) | High (5) | 20 | Agile sprints with localized beta testers; fallback to standard Hindi/English. | Dev Lead |
| R02 | Port congestion delays inventory staging | Med (3) | High (5) | 15 | Buffer 2 weeks in supply chain timeline; use air freight for initial 5k units if needed. | Supply Chain |
| R03 | Retailers demand higher margins | Med (3) | Med (3) | 9 | Pre-approved negotiation matrix with fallback volume discounts. | Sales Lead |
| R04 | Competitor launches similar product | Low (2) | High (4) | 8 | Monitor market intelligence; emphasize Ballie's unique ecosystem integration. | Mktg Lead |

26. Waterfall Methodology Application

The Waterfall methodology is strictly applied to the Distribution & Logistics phase. Physical hardware movement, retailer contract finalization, and customs clearance require sequential, gated approvals. You cannot stage inventory (F) until retailer terms are finalized (D).

27. Agile Project Management Application

Conversely, the Software Localization and Marketing Assets are managed using Agile frameworks (Scrum). Consumer preferences shift rapidly, requiring iterative development.

Table 10: Agile Sprint Plan (Software Localization)

| Sprint | Duration | Goal | Key Deliverables |
| --- | --- | --- | --- |
| Sprint 1 | 2 Weeks | Base Hindi NLP Integration | Core command recognition |
| Sprint 2 | 2 Weeks | Contextual Understanding | Follow-up question capability |
| Sprint 3 | 2 Weeks | SmartThings Ecosystem Link | Controlling ACs/TVs via Hindi |
| Sprint 4 | 2 Weeks | Bug Fixes & Refinement | Reduced latency, UI polish |

Table 11: Product Backlog (Prioritized)

| ID | User Story | Priority | Story Points |
| --- | --- | --- | --- |
| 1 | As a user, I want to ask Ballie to turn on the AC in Hindi. | High | 8 |
| 2 | As a user, I want Ballie to recognize my specific family members. | High | 13 |
| 3 | As a user, I want Ballie to patrol the house when I am away. | Medium | 5 |

28. Waterfall vs Agile Comparison

Strategic Recommendation: A hybrid model (Bimodal IT/Project Management) is optimal. Agile allows the dev team to pivot based on Sprint Review feedback without derailing the rigid, Waterfall-driven supply chain timeline dictated by the immutable Diwali launch date.

29. Earned Value Analysis (EVA)

To assess project health, an EVA was conducted at the end of Week 12 (approximately halfway).

- Total Budget (BAC): ₹40,000,000

- Planned Value (PV): ₹22,000,000 (Value of work scheduled by W12)

- Earned Value (EV): ₹19,500,000 (Value of work actually completed)

- Actual Cost (AC): ₹21,000,000 (Money spent to date)

Table 12: Earned Value Analysis Calculations

| Metric | Formula | Calculation | Result | Interpretation |
| --- | --- | --- | --- | --- |
| Schedule Variance (SV) | EV - PV | 19.5M - 22.0M | -₹2,500,000 | Behind Schedule |
| Cost Variance (CV) | EV - AC | 19.5M - 21.0M | -₹1,500,000 | Over Budget |
| Schedule Performance Index (SPI) | EV / PV | 19.5 / 22.0 | 0.88 | Progressing at 88% of planned rate |
| Cost Performance Index (CPI) | EV / AC | 19.5 / 21.0 | 0.92 | Getting ₹0.92 value for every ₹1 spent |
| Estimate at Completion (EAC) | BAC / CPI | 40M / 0.92 | ₹43,478,260 | Projected final cost if trend continues |

Analytical Interpretation: An SPI of 0.88 and CPI of 0.92 indicates the project is slipping both in time and budget. The root cause (identified in status meetings) was the higher-than-expected cost and time required for Sprint 2 (Contextual NLP). Management must authorize crashing for Phase E (Beta Testing) to recover the schedule, and reallocate underutilized marketing funds to cover the ₹3.47M projected budget overrun.

30. Project Monitoring, Closure, Lessons Learned, and Final Recommendations

Monitoring & Control:

Continuous monitoring will be enforced via Weekly Scrum stand-ups for Agile tracks and bi-weekly variance reports for Waterfall tracks. Any SPI dropping below 0.85 will trigger an automatic steering committee escalation.

Project Closure Phase:

Upon successful launch (Week 24), the project will enter administrative closure.

- Transition software maintenance to the Sustaining Engineering team.

- Release temporary QA and event staff.

- Conduct financial reconciliation and close procurement contracts.

Table 13: Lessons Learned Register

| Category | Finding | Recommendation for Future Projects |
| --- | --- | --- |
| Technical | Hinglish NLP datasets were sparse, causing Sprint 1 delays. | Procure third-party linguistic datasets during the Initiation phase rather than building in-house. |
| Scheduling | Parallel critical paths removed flexibility. | Build larger time buffers into vendor negotiation phases; avoid zero-float dual paths. |
| Budgeting | Localized beta testing required heavy incentives. | Increase the UAT budget baseline by 20% for future regional product rollouts. |

Final Managerial Recommendations:

The Samsung Ballie GTM project demonstrates the complexities of launching AI hardware in a diverse market. To ensure long-term viability post-launch, it is recommended that the project team provisions a "Post-Launch Hypercare" team for the first 30 days to immediately address consumer software bugs. Furthermore, leveraging the Agile backlog will allow continuous Over-The-Air (OTA) updates, converting early adopters into brand advocates and securing Samsung's dominant position in the Indian smart home ecosystem.